Savory Studio - Service Booking Platform

Complete Low-Level Development Activities

1. FRONTEND APPLICATION (React - Admin & Vendor Portals)

1.1 Project Setup & Configuration

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| FE-001 | Initialize React Project | Create React app using Vite or CRA with TypeScript template | 2 |
| FE-002 | Configure Folder Structure | Set up folders: components, pages, services, hooks, utils, assets, styles, types, constants | 2 |
| FE-003 | Install Core Dependencies | Install react-router-dom, axios, react-query/tanstack-query, zustand/redux-toolkit | 2 |
| FE-004 | Install UI Dependencies | Install component library (MUI/Ant Design/Chakra), icons, form library (react-hook-form), validation (yup/zod) | 2 |
| FE-005 | Configure Environment Variables | Set up .env files for development, staging, production with API URLs | 1 |
| FE-006 | Set Up ESLint & Prettier | Configure linting rules, formatting, pre-commit hooks with husky | 2 |
| FE-007 | Configure Path Aliases | Set up absolute imports with tsconfig paths | 1 |
| FE-008 | Set Up Git Repository | Initialize git, create .gitignore, configure branch protection rules | 1 |

1.2 Core Infrastructure Development

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| FE-009 | Create API Client Service | Build axios instance with interceptors for auth tokens, error handling, request/response logging | 4 |
| FE-010 | Implement Auth Token Management | Create token storage (localStorage/secure cookies), refresh token logic, auto-logout on expiry | 4 |
| FE-011 | Build Route Configuration | Set up react-router with public routes, protected routes, role-based route guards | 4 |
| FE-012 | Create Auth Context/Store | Implement authentication state management with user data, login status, permissions | 3 |
| FE-013 | Build Protected Route Component | Create HOC/wrapper for route protection based on auth status and role | 2 |
| FE-014 | Implement Role-Based Access Control | Create permission constants, role checking utilities, conditional rendering helpers | 3 |
| FE-015 | Set Up Global Error Boundary | Create error boundary component with fallback UI and error reporting | 2 |
| FE-016 | Create Toast/Notification System | Implement global notification system for success/error/warning messages | 2 |

1.3 Shared Components Development

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| FE-017 | Build Layout Component | Create main layout with header, sidebar, content area, footer | 4 |
| FE-018 | Create Header Component | Build header with logo, user menu, notifications, logout button | 3 |
| FE-019 | Create Sidebar Navigation | Build collapsible sidebar with role-based menu items, active state indication | 4 |
| FE-020 | Build Form Components | Create reusable input, select, checkbox, radio, textarea, file upload components | 6 |
| FE-021 | Create Data Table Component | Build reusable table with sorting, pagination, filtering, row selection | 8 |
| FE-022 | Build Modal/Dialog Component | Create reusable modal with variants (confirmation, form, info) | 3 |
| FE-023 | Create Loading Components | Build skeleton loaders, spinners, progress indicators | 2 |
| FE-024 | Build Card Components | Create reusable card layouts for displaying service items, stats | 3 |
| FE-025 | Create Search Component | Build search input with debounce, suggestions, filters | 3 |
| FE-026 | Build Pagination Component | Create pagination with page size selector, page navigation | 2 |
| FE-027 | Create Image Upload Component | Build drag-drop image upload with preview, crop, compression | 5 |
| FE-028 | Build Status Badge Component | Create status indicators for pending, approved, rejected states | 1 |

1.4 Authentication Module (Shared - Admin & Vendor)

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| FE-029 | Create Login Page | Build login form with email/phone, password, remember me, forgot password link | 4 |
| FE-030 | Implement Login API Integration | Connect login form to API, handle success/error responses, store tokens | 3 |
| FE-031 | Create Registration Page | Build sign-up form with all required fields, terms acceptance | 5 |
| FE-032 | Implement Registration API Integration | Connect registration form to API, handle validation errors, success redirect | 3 |
| FE-033 | Create Forgot Password Page | Build form for email/phone input, request password reset | 3 |
| FE-034 | Create Reset Password Page | Build form for OTP verification and new password entry | 3 |
| FE-035 | Implement Password Reset Flow | Integrate forgot/reset password APIs, handle token validation | 3 |
| FE-036 | Create Email/Phone Verification Page | Build OTP input screen for account verification | 3 |
| FE-037 | Implement Logout Functionality | Create logout function clearing tokens, redirecting to login | 1 |

1.5 Admin Portal - Dashboard

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| FE-038 | Create Admin Dashboard Page | Build dashboard layout with stats cards, charts, recent activity | 6 |
| FE-039 | Build Statistics Cards | Create cards showing total users, vendors, bookings, revenue | 3 |
| FE-040 | Implement Charts Component | Build charts for bookings trend, revenue analytics using recharts/chart.js | 5 |
| FE-041 | Create Recent Activity Widget | Build widget showing recent bookings, approvals, registrations | 3 |
| FE-042 | Implement Dashboard API Integration | Connect dashboard to analytics APIs, handle data refresh | 3 |

1.6 Admin Portal - User Management

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| FE-043 | Create Users List Page | Build page with data table showing all registered users | 4 |
| FE-044 | Implement User Search & Filters | Add search by name/email, filters by status, registration date | 3 |
| FE-045 | Create User Detail Modal/Page | Build view showing user profile, booking history, activity | 4 |
| FE-046 | Implement User Actions | Add activate/deactivate user, delete user functionality | 3 |
| FE-047 | Create User Edit Form | Build form to update user details by admin | 3 |
| FE-048 | Implement User Management APIs | Connect all user management features to backend APIs | 3 |

1.7 Admin Portal - Vendor Management

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| FE-049 | Create Vendors List Page | Build page with data table showing all vendors | 4 |
| FE-050 | Implement Vendor Search & Filters | Add search, filters by status, category, registration date | 3 |
| FE-051 | Create Vendor Detail Page | Build detailed view with vendor profile, services, earnings | 5 |
| FE-052 | Implement Vendor Approval Flow | Add approve/reject vendor with reason input | 3 |
| FE-053 | Create Vendor Edit Form | Build form to update vendor details | 3 |
| FE-054 | Implement Vendor Management APIs | Connect vendor management features to backend | 3 |

1.8 Admin Portal - Service Item Approval

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| FE-055 | Create Pending Items List Page | Build page showing all services pending approval | 4 |
| FE-056 | Create Service Detail Modal | Build detailed view with images, description, pricing, vendor info | 4 |
| FE-057 | Implement Approval Actions | Add approve/reject buttons with confirmation, rejection reason | 3 |
| FE-058 | Create Approved Items List Page | Build page showing all approved services | 3 |
| FE-059 | Create Rejected Items List Page | Build page with rejected services and reasons | 3 |
| FE-060 | Implement Bulk Approval Actions | Add select multiple items, bulk approve/reject | 4 |
| FE-061 | Implement Service Approval APIs | Connect approval workflow to backend APIs | 3 |

1.9 Admin Portal - Booking Management

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| FE-062 | Create Bookings List Page | Build page with all bookings across platform | 4 |
| FE-063 | Implement Booking Filters | Add filters by status, date range, vendor, user | 3 |
| FE-064 | Create Booking Detail Page | Build detailed view with service info, user, vendor, payment status | 4 |
| FE-065 | Implement Booking Status Update | Add ability to update booking status, issue refunds | 3 |
| FE-066 | Create Booking Analytics View | Build reports for booking trends, cancellations | 4 |
| FE-067 | Implement Booking Management APIs | Connect booking features to backend | 3 |

1.10 Admin Portal - Settings & Configuration

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| FE-068 | Create Admin Profile Page | Build page for admin to update their profile | 3 |
| FE-069 | Create Change Password Page | Build form for password change with validation | 2 |
| FE-070 | Create Platform Settings Page | Build page for configuring platform-wide settings | 4 |
| FE-071 | Create Category Management Page | Build CRUD interface for service categories | 4 |
| FE-072 | Implement Settings APIs | Connect settings features to backend | 2 |

1.11 Vendor Portal - Dashboard

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| FE-073 | Create Vendor Dashboard Page | Build dashboard with earnings, bookings stats, pending items | 5 |
| FE-074 | Build Earnings Summary Cards | Create cards showing total earnings, pending payouts | 3 |
| FE-075 | Create Bookings Overview Widget | Build widget showing recent and upcoming bookings | 3 |
| FE-076 | Implement Vendor Dashboard APIs | Connect dashboard to vendor analytics APIs | 3 |

1.12 Vendor Portal - Service Management

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| FE-077 | Create My Services List Page | Build page showing vendor's uploaded services | 4 |
| FE-078 | Create Add Service Form | Build multi-step form with title, description, images, pricing, availability | 8 |
| FE-079 | Create Edit Service Form | Build form to update existing service details | 4 |
| FE-080 | Implement Service Image Gallery | Add multiple image upload, reorder, delete functionality | 4 |
| FE-081 | Create Service Preview Component | Build preview of how service will appear to users | 3 |
| FE-082 | Implement Service Status Display | Show pending/approved/rejected status with reasons | 2 |
| FE-083 | Create Service Delete Confirmation | Build confirmation dialog for service deletion | 2 |
| FE-084 | Implement Service Management APIs | Connect all service CRUD operations to backend | 4 |

1.13 Vendor Portal - Booking Management

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| FE-085 | Create Vendor Bookings List Page | Build page showing bookings for vendor's services | 4 |
| FE-086 | Implement Booking Filters | Add filters by service, status, date | 3 |
| FE-087 | Create Booking Detail View | Build detailed view with user info, service details | 4 |
| FE-088 | Implement Booking Actions | Add accept/reject booking, mark as complete | 3 |
| FE-089 | Create Booking Calendar View | Build calendar showing bookings schedule | 5 |
| FE-090 | Implement Vendor Booking APIs | Connect booking features to backend | 3 |

1.14 Vendor Portal - Profile & Settings

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| FE-091 | Create Vendor Profile Page | Build page showing vendor's public profile | 4 |
| FE-092 | Create Edit Profile Form | Build form to update business details, contact info, images | 4 |
| FE-093 | Create Bank Details Form | Build form for payment/payout configuration | 3 |
| FE-094 | Create Availability Settings | Build interface to set working hours, holidays | 4 |
| FE-095 | Implement Vendor Profile APIs | Connect profile management to backend | 3 |

1.15 Testing & Quality Assurance

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| FE-096 | Write Unit Tests for Components | Create Jest/Vitest tests for all shared components | 12 |
| FE-097 | Write Integration Tests | Create tests for API integrations and flows | 8 |
| FE-098 | Perform Cross-Browser Testing | Test on Chrome, Firefox, Safari, Edge | 6 |
| FE-099 | Perform Responsive Testing | Test on various screen sizes, devices | 4 |
| FE-100 | Fix Bugs from QA Testing | Address issues identified during testing | 16 |
| FE-101 | Performance Optimization | Optimize bundle size, lazy loading, caching | 8 |
| FE-102 | Accessibility Audit & Fixes | Ensure WCAG compliance, keyboard navigation | 6 |

2. BACKEND APPLICATION (Python FastAPI)

2.1 Project Setup & Configuration

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| BE-001 | Initialize FastAPI Project | Create project structure with main.py, requirements.txt | 2 |
| BE-002 | Configure Project Structure | Set up folders: api, core, models, schemas, services, utils, tests | 2 |
| BE-003 | Install Core Dependencies | Install fastapi, uvicorn, sqlalchemy, alembic, pydantic | 2 |
| BE-004 | Install Additional Dependencies | Install python-jose, passlib, python-multipart, boto3, stripe | 2 |
| BE-005 | Configure Environment Management | Set up python-dotenv, create .env templates for all environments | 2 |
| BE-006 | Set Up Database Connection | Configure SQLAlchemy engine, session management | 3 |
| BE-007 | Configure Alembic Migrations | Initialize Alembic, configure migration environment | 2 |
| BE-008 | Set Up Logging Configuration | Configure structured logging with rotation | 2 |
| BE-009 | Configure CORS Middleware | Set up CORS for frontend origins | 1 |
| BE-010 | Set Up Git Repository | Initialize git, create .gitignore, configure hooks | 1 |

2.2 Database Design & Models

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| BE-011 | Design Database Schema | Create ERD with all tables, relationships, indexes | 6 |
| BE-012 | Create User Model | Define user table with all fields, constraints | 2 |
| BE-013 | Create Vendor Model | Define vendor table with business details, verification status | 2 |
| BE-014 | Create Admin Model | Define admin table with role, permissions | 2 |
| BE-015 | Create Service Category Model | Define categories table with hierarchy support | 2 |
| BE-016 | Create Service Item Model | Define services table with all attributes, foreign keys | 3 |
| BE-017 | Create Service Image Model | Define images table linked to services | 2 |
| BE-018 | Create Booking Model | Define bookings table with status, timestamps | 3 |
| BE-019 | Create Payment Model | Define payments table with transaction details | 3 |
| BE-020 | Create Review Model | Define reviews table for user ratings | 2 |
| BE-021 | Create Notification Model | Define notifications table for all roles | 2 |
| BE-022 | Create Audit Log Model | Define audit trail table for tracking changes | 2 |
| BE-023 | Create Initial Migration | Generate Alembic migration for all models | 2 |
| BE-024 | Create Seed Data Script | Build script for initial categories, admin user | 3 |

2.3 Core Infrastructure

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| BE-025 | Create Base Repository Pattern | Build generic CRUD repository class | 4 |
| BE-026 | Implement Dependency Injection | Set up FastAPI dependencies for DB, auth, services | 3 |
| BE-027 | Create Custom Exception Classes | Define application-specific exceptions | 2 |
| BE-028 | Build Global Exception Handler | Create middleware for consistent error responses | 3 |
| BE-029 | Create Response Schema Classes | Define standard API response formats | 2 |
| BE-030 | Build Pagination Utilities | Create pagination helper functions, schemas | 2 |
| BE-031 | Implement Request Validation | Set up Pydantic validators, custom validators | 3 |
| BE-032 | Create File Upload Utilities | Build helpers for S3/local file storage | 4 |
| BE-033 | Implement Email Service | Create email sending service with templates | 4 |
| BE-034 | Create SMS Service | Build SMS sending service for OTP | 3 |
| BE-035 | Build Background Task Queue | Set up Celery/FastAPI background tasks | 4 |

2.4 Authentication & Authorization

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| BE-036 | Create Auth Schemas | Define request/response schemas for auth endpoints | 2 |
| BE-037 | Implement Password Hashing | Create utilities for password hash/verify using bcrypt | 2 |
| BE-038 | Implement JWT Token Generation | Build access token and refresh token creation | 3 |
| BE-039 | Create JWT Token Validation | Build token verification, decode utilities | 2 |
| BE-040 | Build User Registration API | Create POST /auth/register endpoint | 4 |
| BE-041 | Implement Email Verification | Create verification token generation, email sending | 3 |
| BE-042 | Build Login API | Create POST /auth/login endpoint with token response | 3 |
| BE-043 | Implement Refresh Token API | Create POST /auth/refresh endpoint | 2 |
| BE-044 | Build Forgot Password API | Create POST /auth/forgot-password endpoint | 3 |
| BE-045 | Implement Reset Password API | Create POST /auth/reset-password endpoint | 3 |
| BE-046 | Create Change Password API | Create POST /auth/change-password endpoint | 2 |
| BE-047 | Build Logout API | Create POST /auth/logout with token blacklisting | 2 |
| BE-048 | Implement Auth Middleware | Create dependency for route protection | 3 |
| BE-049 | Create Role-Based Authorization | Build permission checking decorators/dependencies | 3 |
| BE-050 | Implement Rate Limiting | Add rate limiting for auth endpoints | 2 |

2.5 User Management APIs

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| BE-051 | Create User Schemas | Define all user-related request/response schemas | 2 |
| BE-052 | Build User Service Layer | Create UserService class with business logic | 4 |
| BE-053 | Create Get User Profile API | Create GET /users/me endpoint | 2 |
| BE-054 | Build Update User Profile API | Create PUT /users/me endpoint | 3 |
| BE-055 | Create Upload Profile Image API | Create POST /users/me/avatar endpoint | 3 |
| BE-056 | Build List Users API (Admin) | Create GET /admin/users with pagination, filters | 4 |
| BE-057 | Create Get User by ID API (Admin) | Create GET /admin/users/{id} endpoint | 2 |
| BE-058 | Build Update User Status API (Admin) | Create PUT /admin/users/{id}/status endpoint | 2 |
| BE-059 | Create Delete User API (Admin) | Create DELETE /admin/users/{id} endpoint | 2 |

2.6 Vendor Management APIs

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| BE-060 | Create Vendor Schemas | Define vendor-related request/response schemas | 2 |
| BE-061 | Build Vendor Service Layer | Create VendorService class with business logic | 4 |
| BE-062 | Create Vendor Registration API | Create POST /vendors/register endpoint | 4 |
| BE-063 | Build Get Vendor Profile API | Create GET /vendors/me endpoint | 2 |
| BE-064 | Create Update Vendor Profile API | Create PUT /vendors/me endpoint | 3 |
| BE-065 | Build Upload Vendor Documents API | Create POST /vendors/me/documents endpoint | 3 |
| BE-066 | Create List Vendors API (Admin) | Create GET /admin/vendors with pagination, filters | 4 |
| BE-067 | Build Get Vendor by ID API (Admin) | Create GET /admin/vendors/{id} endpoint | 2 |
| BE-068 | Create Approve Vendor API (Admin) | Create POST /admin/vendors/{id}/approve endpoint | 3 |
| BE-069 | Build Reject Vendor API (Admin) | Create POST /admin/vendors/{id}/reject endpoint | 3 |
| BE-070 | Create Vendor Analytics API | Create GET /vendors/me/analytics endpoint | 4 |

2.7 Service Category APIs

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| BE-071 | Create Category Schemas | Define category request/response schemas | 2 |
| BE-072 | Build Category Service Layer | Create CategoryService class | 3 |
| BE-073 | Create List Categories API | Create GET /categories endpoint | 2 |
| BE-074 | Build Get Category by ID API | Create GET /categories/{id} endpoint | 2 |
| BE-075 | Create Add Category API (Admin) | Create POST /admin/categories endpoint | 2 |
| BE-076 | Build Update Category API (Admin) | Create PUT /admin/categories/{id} endpoint | 2 |
| BE-077 | Create Delete Category API (Admin) | Create DELETE /admin/categories/{id} endpoint | 2 |

2.8 Service Item APIs

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| BE-078 | Create Service Schemas | Define service item request/response schemas | 3 |
| BE-079 | Build Service Item Service Layer | Create ServiceItemService class | 5 |
| BE-080 | Create Add Service API (Vendor) | Create POST /vendors/services endpoint | 4 |
| BE-081 | Build Upload Service Images API | Create POST /vendors/services/{id}/images endpoint | 4 |
| BE-082 | Create Get Vendor Services API | Create GET /vendors/me/services endpoint | 3 |
| BE-083 | Build Update Service API (Vendor) | Create PUT /vendors/services/{id} endpoint | 3 |
| BE-084 | Create Delete Service API (Vendor) | Create DELETE /vendors/services/{id} endpoint | 2 |
| BE-085 | Build List All Services API (User) | Create GET /services with pagination, filters, search | 5 |
| BE-086 | Create Get Service Detail API | Create GET /services/{id} endpoint | 2 |
| BE-087 | Build Services by Category API | Create GET /services/category/{id} endpoint | 3 |
| BE-088 | Create Nearby Services API | Create GET /services/nearby with geolocation | 5 |
| BE-089 | Build Pending Services API (Admin) | Create GET /admin/services/pending endpoint | 3 |
| BE-090 | Create Approve Service API (Admin) | Create POST /admin/services/{id}/approve endpoint | 3 |
| BE-091 | Build Reject Service API (Admin) | Create POST /admin/services/{id}/reject endpoint | 3 |
| BE-092 | Create Service Search API | Create GET /services/search with full-text search | 4 |

2.9 Booking APIs

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| BE-093 | Create Booking Schemas | Define booking request/response schemas | 3 |
| BE-094 | Build Booking Service Layer | Create BookingService class with business logic | 6 |
| BE-095 | Create Check Availability API | Create GET /services/{id}/availability endpoint | 4 |
| BE-096 | Build Create Booking API | Create POST /bookings endpoint | 5 |
| BE-097 | Create Get User Bookings API | Create GET /users/me/bookings endpoint | 3 |
| BE-098 | Build Get Booking Detail API | Create GET /bookings/{id} endpoint | 2 |
| BE-099 | Create Cancel Booking API | Create POST /bookings/{id}/cancel endpoint | 3 |
| BE-100 | Build Get Vendor Bookings API | Create GET /vendors/me/bookings endpoint | 3 |
| BE-101 | Create Accept Booking API (Vendor) | Create POST /vendors/bookings/{id}/accept endpoint | 3 |
| BE-102 | Build Reject Booking API (Vendor) | Create POST /vendors/bookings/{id}/reject endpoint | 3 |
| BE-103 | Create Complete Booking API | Create POST /bookings/{id}/complete endpoint | 3 |
| BE-104 | Build All Bookings API (Admin) | Create GET /admin/bookings with filters | 4 |
| BE-105 | Create Booking Statistics API | Create GET /admin/bookings/stats endpoint | 4 |

2.10 Payment Integration

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| BE-106 | Create Payment Schemas | Define payment request/response schemas | 2 |
| BE-107 | Build Payment Service Layer | Create PaymentService class | 4 |
| BE-108 | Integrate Payment Gateway SDK | Set up Stripe/Razorpay SDK configuration | 4 |
| BE-109 | Create Initiate Payment API | Create POST /payments/initiate endpoint | 4 |
| BE-110 | Build Payment Webhook Handler | Create POST /webhooks/payment endpoint | 5 |
| BE-111 | Create Verify Payment API | Create POST /payments/verify endpoint | 3 |
| BE-112 | Build Get Payment History API | Create GET /users/me/payments endpoint | 3 |
| BE-113 | Create Refund API | Create POST /payments/{id}/refund endpoint | 4 |
| BE-114 | Build Vendor Payout Logic | Create payout calculation and processing | 5 |
| BE-115 | Create Payment Reports API (Admin) | Create GET /admin/payments/reports endpoint | 4 |

2.11 Reviews & Ratings APIs

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| BE-116 | Create Review Schemas | Define review request/response schemas | 2 |
| BE-117 | Build Review Service Layer | Create ReviewService class | 3 |
| BE-118 | Create Add Review API | Create POST /bookings/{id}/review endpoint | 3 |
| BE-119 | Build Get Service Reviews API | Create GET /services/{id}/reviews endpoint | 3 |
| BE-120 | Create Get Vendor Reviews API | Create GET /vendors/{id}/reviews endpoint | 2 |
| BE-121 | Build Update Review API | Create PUT /reviews/{id} endpoint | 2 |
| BE-122 | Create Delete Review API | Create DELETE /reviews/{id} endpoint | 2 |

2.12 Notification System

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| BE-123 | Create Notification Schemas | Define notification schemas | 2 |
| BE-124 | Build Notification Service | Create NotificationService class | 4 |
| BE-125 | Implement Push Notification Integration | Set up Firebase Cloud Messaging | 5 |
| BE-126 | Create Get Notifications API | Create GET /notifications endpoint | 2 |
| BE-127 | Build Mark as Read API | Create PUT /notifications/{id}/read endpoint | 2 |
| BE-128 | Create Notification Triggers | Implement event-based notification sending | 4 |

2.13 Admin Dashboard APIs

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| BE-129 | Create Dashboard Schemas | Define dashboard data schemas | 2 |
| BE-130 | Build Dashboard Statistics API | Create GET /admin/dashboard/stats endpoint | 4 |
| BE-131 | Create Revenue Analytics API | Create GET /admin/dashboard/revenue endpoint | 4 |
| BE-132 | Build User Growth Analytics API | Create GET /admin/dashboard/users endpoint | 3 |
| BE-133 | Create Booking Analytics API | Create GET /admin/dashboard/bookings endpoint | 3 |
| BE-134 | Build Recent Activity API | Create GET /admin/dashboard/activity endpoint | 3 |

2.14 Testing & Documentation

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| BE-135 | Write Unit Tests for Services | Create pytest tests for all service classes | 16 |
| BE-136 | Write Integration Tests for APIs | Create tests for all API endpoints | 16 |
| BE-137 | Create API Documentation | Configure OpenAPI/Swagger documentation | 4 |
| BE-138 | Write Postman Collection | Create Postman collection for all endpoints | 4 |
| BE-139 | Performance Testing | Load test critical endpoints | 6 |
| BE-140 | Security Testing | Test for common vulnerabilities (OWASP) | 6 |
| BE-141 | Fix Bugs from Testing | Address issues found during testing | 16 |

3. MOBILE APPLICATION (Ionic - User App)

3.1 Project Setup & Configuration

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| MB-001 | Initialize Ionic Project | Create Ionic Angular/React project with Capacitor | 2 |
| MB-002 | Configure Project Structure | Set up folders: pages, components, services, guards, pipes, models | 2 |
| MB-003 | Install Core Dependencies | Install @ionic/angular, @capacitor/core, @capacitor plugins | 2 |
| MB-004 | Install Additional Packages | Install axios/http client, storage, native plugins | 2 |
| MB-005 | Configure Environment Files | Set up environment.ts for dev, staging, prod | 1 |
| MB-006 | Set Up Native Plugins | Configure camera, geolocation, push notifications | 3 |
| MB-007 | Configure App Icons & Splash | Set up app icon and splash screen resources | 2 |
| MB-008 | Set Up Git Repository | Initialize git with proper .gitignore | 1 |

3.2 Core Infrastructure

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| MB-009 | Create API Service | Build HTTP client service with interceptors | 4 |
| MB-010 | Implement Token Storage | Create secure storage for auth tokens | 3 |
| MB-011 | Build Auth Guard | Create route guard for protected pages | 2 |
| MB-012 | Create Auth State Management | Implement auth state with storage persistence | 3 |
| MB-013 | Build Error Handling Service | Create global error handler with toast notifications | 3 |
| MB-014 | Implement Offline Detection | Create service to detect and handle offline state | 3 |
| MB-015 | Build Loading Service | Create reusable loading indicator service | 2 |
| MB-016 | Create Navigation Service | Build navigation helper with history management | 2 |

3.3 Shared Components

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| MB-017 | Create Custom Header Component | Build app header with back button, title, actions | 3 |
| MB-018 | Build Tab Bar Component | Create bottom navigation tab bar | 3 |
| MB-019 | Create Service Card Component | Build card for displaying service items | 4 |
| MB-020 | Build Category Card Component | Create category selection cards | 2 |
| MB-021 | Create Search Bar Component | Build search input with voice search option | 3 |
| MB-022 | Build Rating Component | Create star rating display and input | 2 |
| MB-023 | Create Image Carousel Component | Build swipeable image gallery | 4 |
| MB-024 | Build Empty State Component | Create empty state for lists with illustration | 2 |
| MB-025 | Create Pull-to-Refresh Component | Build refresh functionality for lists | 2 |
| MB-026 | Build Skeleton Loader Components | Create skeleton loaders for cards, lists | 3 |

3.4 Authentication Screens

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| MB-027 | Create Onboarding Screens | Build intro slides for first-time users | 4 |
| MB-028 | Build Login Screen | Create login form with email/phone, password | 4 |
| MB-029 | Implement Login API Integration | Connect login to backend, handle tokens | 3 |
| MB-030 | Create Registration Screen | Build sign-up form with all required fields | 5 |
| MB-031 | Implement Registration API Integration | Connect registration to backend | 3 |
| MB-032 | Build Phone Verification Screen | Create OTP input screen | 3 |
| MB-033 | Implement OTP Verification | Connect OTP verification to backend | 2 |
| MB-034 | Create Forgot Password Screen | Build forgot password form | 3 |
| MB-035 | Build Reset Password Screen | Create new password entry screen | 3 |
| MB-036 | Implement Password Reset Flow | Connect reset password APIs | 2 |
| MB-037 | Create Social Login Integration | Implement Google/Apple sign-in | 6 |

3.5 Home & Discovery Screens

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| MB-038 | Create Home Screen | Build main home page with categories, featured services | 6 |
| MB-039 | Build Location Permission Handler | Request and handle location permissions | 3 |
| MB-040 | Create Location Selection Screen | Build screen to select/change delivery location | 4 |
| MB-041 | Implement Home API Integration | Connect home screen to backend APIs | 3 |
| MB-042 | Build Category Listing Screen | Create screen showing all categories | 3 |
| MB-043 | Create Services by Category Screen | Build list of services for selected category | 4 |
| MB-044 | Implement Category APIs | Connect category screens to backend | 2 |
| MB-045 | Build Featured Services Section | Create horizontal scrollable featured items | 3 |
| MB-046 | Create Nearby Services Section | Build section showing services near user | 4 |

3.6 Search & Filters

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| MB-047 | Create Search Screen | Build dedicated search page | 4 |
| MB-048 | Implement Search Suggestions | Add recent searches, popular suggestions | 3 |
| MB-049 | Build Search Results Screen | Create results listing with pagination | 4 |
| MB-050 | Create Filter Bottom Sheet | Build filters for category, price, rating, distance | 5 |
| MB-051 | Implement Sort Options | Add sorting by price, rating, distance | 2 |
| MB-052 | Build Search API Integration | Connect search to backend | 3 |

3.7 Service Detail & Booking

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| MB-053 | Create Service Detail Screen | Build detailed service page with all info | 6 |
| MB-054 | Build Image Gallery Viewer | Create full-screen image viewer with zoom | 4 |
| MB-055 | Create Vendor Info Section | Build section showing vendor details | 3 |
| MB-056 | Build Reviews Section | Create reviews list with rating summary | 4 |
| MB-057 | Implement Service Detail APIs | Connect to backend for service data | 2 |
| MB-058 | Create Date/Time Picker | Build booking date and time selection | 5 |
| MB-059 | Build Booking Summary Screen | Create order summary before payment | 4 |
| MB-060 | Implement Check Availability API | Connect availability checking to backend | 3 |
| MB-061 | Create Booking Confirmation Screen | Build success screen after booking | 3 |
| MB-062 | Implement Create Booking API | Connect booking creation to backend | 3 |

3.8 Payment Integration

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| MB-063 | Create Payment Method Selection | Build screen to select payment method | 4 |
| MB-064 | Integrate Payment Gateway SDK | Set up Stripe/Razorpay native SDK | 6 |
| MB-065 | Build Payment Processing Screen | Create payment in-progress screen | 3 |
| MB-066 | Implement Payment Success/Failure | Handle payment result screens | 3 |
| MB-067 | Create Add Card Screen | Build form to add new payment card | 4 |
| MB-068 | Implement Saved Cards | Show and manage saved payment methods | 3 |
| MB-069 | Connect Payment APIs | Integrate payment initiation and verification | 4 |

3.9 Bookings Management

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| MB-070 | Create My Bookings Screen | Build bookings list with tabs (upcoming, past) | 5 |
| MB-071 | Build Booking Detail Screen | Create detailed view of single booking | 4 |
| MB-072 | Implement Booking Status Tracking | Show real-time booking status updates | 4 |
| MB-073 | Create Cancel Booking Flow | Build cancellation with reason selection | 3 |
| MB-074 | Build Reschedule Booking Flow | Create date/time modification | 4 |
| MB-075 | Implement Bookings API Integration | Connect all booking features to backend | 3 |
| MB-076 | Create Booking Notifications | Handle push notifications for booking updates | 3 |

3.10 Reviews & Ratings

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| MB-077 | Create Write Review Screen | Build review form with rating, text, images | 4 |
| MB-078 | Build Review Submission | Implement review API integration | 2 |
| MB-079 | Create My Reviews Screen | Build list of user's submitted reviews | 3 |
| MB-080 | Implement Edit Review | Create edit functionality for reviews | 2 |

3.11 User Profile

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| MB-081 | Create Profile Screen | Build user profile page with menu options | 4 |
| MB-082 | Build Edit Profile Screen | Create form to update user details | 4 |
| MB-083 | Create Profile Photo Upload | Implement camera/gallery image selection | 3 |
| MB-084 | Build Saved Addresses Screen | Create address management CRUD | 5 |
| MB-085 | Create Add Address Screen | Build address form with map selection | 4 |
| MB-086 | Implement Profile APIs | Connect profile features to backend | 3 |

3.12 Notifications

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| MB-087 | Create Notifications Screen | Build notifications list page | 4 |
| MB-088 | Implement Push Notification Handler | Set up FCM and notification handling | 5 |
| MB-089 | Build Notification Deep Linking | Navigate to relevant screen on notification tap | 4 |
| MB-090 | Create Notification Settings | Build preferences for notification types | 3 |
| MB-091 | Implement Notifications API | Connect to backend for notifications | 2 |

3.13 Settings & Support

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| MB-092 | Create Settings Screen | Build settings page with all options | 3 |
| MB-093 | Build Change Password Screen | Create password change form | 3 |
| MB-094 | Create Help & Support Screen | Build FAQ, contact support options | 3 |
| MB-095 | Build About Screen | Create app info, version, legal links | 2 |
| MB-096 | Create Privacy Policy Screen | Build privacy policy display | 1 |
| MB-097 | Build Terms of Service Screen | Create terms display | 1 |
| MB-098 | Implement Logout Flow | Create logout with confirmation | 2 |
| MB-099 | Create Delete Account Flow | Build account deletion request | 3 |

3.14 Testing & Optimization

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| MB-100 | Write Unit Tests | Create tests for services and components | 12 |
| MB-101 | Perform Device Testing (Android) | Test on multiple Android devices/versions | 8 |
| MB-102 | Perform Device Testing (iOS) | Test on multiple iOS devices/versions | 8 |
| MB-103 | Fix Platform-Specific Issues | Address Android/iOS specific bugs | 10 |
| MB-104 | Performance Optimization | Optimize images, lazy loading, bundle size | 6 |
| MB-105 | Memory Leak Testing | Identify and fix memory leaks | 4 |
| MB-106 | Battery Usage Optimization | Optimize background processes | 4 |
| MB-107 | Fix Bugs from QA | Address all issues from testing | 16 |

4. CLOUD INFRASTRUCTURE SETUP (AWS)

4.1 AWS Account & Organization Setup

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| INF-001 | Configure AWS Organization | Set up AWS organization with OUs | 2 |
| INF-002 | Create AWS Accounts | Create accounts for dev, staging, production | 2 |
| INF-003 | Set Up IAM Users & Groups | Create admin users, developer groups | 3 |
| INF-004 | Configure IAM Policies | Create custom policies for each role | 4 |
| INF-005 | Enable MFA | Enable MFA for all IAM users | 1 |
| INF-006 | Set Up AWS SSO | Configure SSO for team access | 3 |
| INF-007 | Configure Billing Alerts | Set up budget alerts and cost monitoring | 2 |
| INF-008 | Enable CloudTrail | Set up audit logging for all accounts | 2 |

4.2 Networking Setup

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| INF-009 | Create VPC | Set up VPC with appropriate CIDR block | 2 |
| INF-010 | Create Subnets | Create public and private subnets across AZs | 3 |
| INF-011 | Configure Internet Gateway | Set up IGW for public subnet access | 1 |
| INF-012 | Create NAT Gateway | Set up NAT for private subnet outbound | 2 |
| INF-013 | Configure Route Tables | Set up routing for public and private subnets | 2 |
| INF-014 | Create Security Groups | Define security groups for each service tier | 4 |
| INF-015 | Set Up Network ACLs | Configure network ACLs for added security | 2 |
| INF-016 | Configure VPC Flow Logs | Enable flow logs for network monitoring | 1 |

4.3 Database Setup

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| INF-017 | Create RDS Subnet Group | Set up subnet group for RDS | 1 |
| INF-018 | Launch RDS PostgreSQL | Create RDS PostgreSQL instance | 3 |
| INF-019 | Configure RDS Security | Set up security groups, encryption | 2 |
| INF-020 | Enable RDS Backups | Configure automated backups, retention | 1 |
| INF-021 | Set Up Read Replica | Create read replica for production | 2 |
| INF-022 | Create ElastiCache Redis | Set up Redis for caching and sessions | 3 |
| INF-023 | Configure Database Users | Create application database users | 2 |
| INF-024 | Set Up Database Monitoring | Configure CloudWatch for RDS metrics | 2 |

4.4 Compute Setup

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| INF-025 | Create ECR Repositories | Set up container registries for services | 2 |
| INF-026 | Create ECS Cluster | Set up Fargate cluster for containers | 3 |
| INF-027 | Create Task Definitions | Define ECS tasks for backend service | 3 |
| INF-028 | Create ECS Service | Set up ECS service with auto-scaling | 3 |
| INF-029 | Configure Service Auto-Scaling | Set up auto-scaling policies | 2 |
| INF-030 | Create Application Load Balancer | Set up ALB for backend service | 3 |
| INF-031 | Configure ALB Target Groups | Set up target groups for ECS service | 2 |
| INF-032 | Configure Health Checks | Set up health check endpoints | 1 |

4.5 Storage Setup

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| INF-033 | Create S3 Buckets | Set up buckets for uploads, assets, backups | 3 |
| INF-034 | Configure S3 Bucket Policies | Set up access policies and CORS | 2 |
| INF-035 | Enable S3 Versioning | Configure versioning for important buckets | 1 |
| INF-036 | Set Up S3 Lifecycle Rules | Configure lifecycle policies for cost optimization | 2 |
| INF-037 | Configure CloudFront | Set up CDN for static assets | 3 |
| INF-038 | Configure CloudFront SSL | Set up HTTPS with ACM certificate | 2 |

4.6 Frontend Hosting

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| INF-039 | Create S3 Bucket for Web | Set up bucket for React app hosting | 2 |
| INF-040 | Configure Static Website Hosting | Enable S3 static website hosting | 1 |
| INF-041 | Create CloudFront Distribution | Set up CDN for web app | 3 |
| INF-042 | Configure Custom Domain | Set up Route 53 for custom domain | 2 |
| INF-043 | Create SSL Certificate | Generate ACM certificate for domain | 1 |
| INF-044 | Configure DNS Records | Set up A, CNAME records in Route 53 | 1 |

4.7 CI/CD Pipeline Setup

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| INF-045 | Create GitHub Repository | Set up repo with branch protection | 2 |
| INF-046 | Configure GitHub Actions | Create workflow files for CI/CD | 6 |
| INF-047 | Create Backend CI Pipeline | Build, test, push Docker image | 4 |
| INF-048 | Create Backend CD Pipeline | Deploy to ECS from GitHub Actions | 4 |
| INF-049 | Create Frontend CI Pipeline | Build, test React app | 3 |
| INF-050 | Create Frontend CD Pipeline | Deploy to S3, invalidate CloudFront | 3 |
| INF-051 | Create Mobile CI Pipeline | Build Android and iOS apps | 5 |
| INF-052 | Configure Secrets Management | Set up GitHub secrets, AWS Secrets Manager | 3 |
| INF-053 | Create Staging Pipeline | Set up separate pipeline for staging | 3 |
| INF-054 | Create Production Pipeline | Set up production deployment with approvals | 3 |

4.8 Monitoring & Logging

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| INF-055 | Set Up CloudWatch Log Groups | Create log groups for all services | 2 |
| INF-056 | Configure CloudWatch Alarms | Set up alarms for critical metrics | 4 |
| INF-057 | Create CloudWatch Dashboard | Build dashboard for service monitoring | 3 |
| INF-058 | Set Up X-Ray Tracing | Configure distributed tracing | 3 |
| INF-059 | Configure SNS Notifications | Set up alert notifications to team | 2 |
| INF-060 | Set Up Application Logs | Configure structured logging to CloudWatch | 2 |

4.9 Security Configuration

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| INF-061 | Configure WAF | Set up Web Application Firewall | 4 |
| INF-062 | Enable AWS Shield | Configure DDoS protection | 2 |
| INF-063 | Set Up AWS Secrets Manager | Store database credentials, API keys | 3 |
| INF-064 | Configure Parameter Store | Store application configuration | 2 |
| INF-065 | Enable GuardDuty | Set up threat detection | 2 |
| INF-066 | Configure Security Hub | Enable security findings aggregation | 2 |
| INF-067 | Set Up KMS Keys | Create encryption keys for services | 2 |

4.10 Environment Replication

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| INF-068 | Create Terraform Modules | Build reusable infrastructure modules | 8 |
| INF-069 | Create Development Environment | Deploy full stack for dev | 4 |
| INF-070 | Create Staging Environment | Deploy full stack for staging | 4 |
| INF-071 | Create Production Environment | Deploy full stack for production | 4 |
| INF-072 | Configure Environment Variables | Set up env-specific configurations | 2 |
| INF-073 | Document Infrastructure | Create infrastructure documentation | 4 |

5. APP STORE DEPLOYMENT (Play Store & App Store)

5.1 Pre-Deployment Preparation

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| DEP-001 | Create App Icons | Generate all required icon sizes for both platforms | 3 |
| DEP-002 | Create App Screenshots | Capture screenshots for all required device sizes | 4 |
| DEP-003 | Create Feature Graphic | Design promotional graphics for store listings | 2 |
| DEP-004 | Write App Description | Create compelling store descriptions | 2 |
| DEP-005 | Prepare Privacy Policy | Create privacy policy page/document | 3 |
| DEP-006 | Prepare Terms of Service | Create terms of service document | 2 |
| DEP-007 | Create App Demo Video | Record app promotional video | 4 |

5.2 Google Play Store Deployment

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| DEP-008 | Create Google Play Developer Account | Set up developer account ($25 one-time fee) | 1 |
| DEP-009 | Create App in Play Console | Set up new app in Google Play Console | 1 |
| DEP-010 | Complete Store Listing | Fill in all listing details, screenshots, description | 3 |
| DEP-011 | Generate Release Keystore | Create signing keystore for Android | 1 |
| DEP-012 | Configure App Signing | Set up Play App Signing | 1 |
| DEP-013 | Build Release APK/AAB | Generate signed Android App Bundle | 2 |
| DEP-014 | Complete Content Rating | Fill out content rating questionnaire | 1 |
| DEP-015 | Set Up Pricing & Distribution | Configure pricing, countries, device targeting | 1 |
| DEP-016 | Complete Data Safety Form | Fill out data collection and usage details | 2 |
| DEP-017 | Upload to Internal Testing | Deploy to internal testing track | 1 |
| DEP-018 | Conduct Internal Testing | Test the distributed build | 4 |
| DEP-019 | Upload to Closed Testing | Deploy to closed beta testing | 1 |
| DEP-020 | Conduct Beta Testing | Gather feedback from beta testers | 8 |
| DEP-021 | Fix Beta Issues | Address issues found in beta | 8 |
| DEP-022 | Upload to Production | Deploy to production track | 1 |
| DEP-023 | Submit for Review | Submit app for Google review | 1 |
| DEP-024 | Address Review Feedback | Fix any issues raised in review | 4 |
| DEP-025 | Go Live on Play Store | Release app to production | 1 |

5.3 Apple App Store Deployment

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| DEP-026 | Create Apple Developer Account | Set up developer account ($99/year) | 2 |
| DEP-027 | Create App ID | Register App ID in Apple Developer Portal | 1 |
| DEP-028 | Create Provisioning Profiles | Set up development and distribution profiles | 2 |
| DEP-029 | Configure Push Notifications | Set up APNs keys and certificates | 2 |
| DEP-030 | Create App in App Store Connect | Set up new app in App Store Connect | 1 |
| DEP-031 | Complete App Information | Fill in all required app details | 2 |
| DEP-032 | Upload App Screenshots | Upload screenshots for all device sizes | 2 |
| DEP-033 | Write App Store Description | Enter description, keywords, what's new | 2 |
| DEP-034 | Configure App Privacy | Complete privacy nutrition labels | 2 |
| DEP-035 | Build Release IPA | Create signed iOS build | 2 |
| DEP-036 | Upload to App Store Connect | Upload build via Xcode/Transporter | 1 |
| DEP-037 | Submit to TestFlight | Deploy for internal testing | 1 |
| DEP-038 | Conduct TestFlight Testing | Test on multiple iOS devices | 6 |
| DEP-039 | Invite External Testers | Add beta testers to TestFlight | 1 |
| DEP-040 | Conduct External Beta | Gather feedback from external testers | 8 |
| DEP-041 | Fix Beta Issues | Address issues found in beta testing | 8 |
| DEP-042 | Prepare for Submission | Complete all submission requirements | 2 |
| DEP-043 | Submit for App Review | Submit app for Apple review | 1 |
| DEP-044 | Address Review Rejection | Fix issues if app is rejected | 6 |
| DEP-045 | Go Live on App Store | Release app to App Store | 1 |

5.4 Post-Deployment Activities

| Activity ID | Activity | Description | Estimated Hours |
| --- | --- | --- | --- |
| DEP-046 | Monitor Store Analytics | Set up and monitor download analytics | 2 |
| DEP-047 | Set Up Review Monitoring | Monitor and respond to user reviews | 2 |
| DEP-048 | Configure Crash Reporting | Set up Firebase Crashlytics integration | 3 |
| DEP-049 | Create Update Release Process | Document process for releasing updates | 2 |
| DEP-050 | Set Up A/B Testing | Configure store listing experiments | 2 |
| DEP-051 | Create ASO Strategy | Develop app store optimization plan | 4 |
| DEP-052 | Document Deployment Process | Create runbook for future deployments | 3 |

Summary

| Track | Total Activities | Estimated Total Hours |
| --- | --- | --- |
| Frontend (React) | 102 | ~350 hours |
| Backend (FastAPI) | 141 | ~450 hours |
| Mobile (Ionic) | 107 | ~380 hours |
| Infrastructure (AWS) | 73 | ~220 hours |
| App Store Deployment | 52 | ~130 hours |
| TOTAL | 475 | ~1,530 hours |